## Example Punch List
Item # | Location | Trade | Description | Assigned To | Due Date | Status | Photo Ref | Verified By
1 | Kitchen | Electrical | GFCI receptacle right of sink fails trip test; replace device and retest | Mike R. | 2026-07-22 | Verified | IMG_0412 | J. Alvarez
2 | Master bath | Plumbing | Tub spout drips after hard shutoff; replace cartridge and verify dry at base | Dave T. | 2026-07-22 | Complete | IMG_0415
3 | Great room | Paint | Flashing over patch left of fireplace; spot-prime and recoat wall corner to corner | ProCoat crew | 2026-07-24 | In Progress | IMG_0418
4 | Hall bath | Tile | Lippage at shower threshold exceeds 1/16 in.; grind or reset two tiles at edge | L. Nguyen | 2026-07-25 | Open | IMG_0421
5 | Bedroom 2 | HVAC | Supply register rattles at high fan; reseat boot and screw flange to drywall | ComfortAir | 2026-07-23 | Complete | IMG_0424
6 | Garage | Drywall | Corner bead crack at man door; tape, refinish, and match texture | S. Patel | 2026-07-27 | Open | IMG_0427
7 | Exterior - front | Gutters | Downspout not terminated to splash block; extend and confirm drainage away from slab | Mike R. | 2026-07-24 | In Progress | IMG_0430
8 | Laundry | Plumbing | Washer box hammer on cold shutoff; install arrestor and retest | Dave T. | 2026-07-25 | Open | IMG_0433
9 | Dining room | Flooring | Transition strip proud at hallway; refasten flush, no trip edge | FloorWorks | 2026-07-26 | Open | IMG_0436
10 | Entry | Doors/Hardware | Front door deadbolt binds at strike; adjust strike plate and confirm smooth key turn | S. Patel | 2026-07-23 | Verified | IMG_0439 | J. Alvarez

## Punch List (Blank)
Item # | Location | Trade | Description | Assigned To | Due Date | Status | Photo Ref | Verified By